# AfyaConnect HIE — Outstanding Integration & Effort

AZ CarePlus HMIS · Progress to witness UAT

2026-10-26

Table of Contents

# AfyaConnect / DHA integration — outstanding work & effort

Product: AZ CarePlus HMIS · UAT: https://hmis.azimkim.co.ke/hmis/
Full matrix (everything): DHA_AFYACONNECT_INTEGRATION_COVERAGE.md
Build phases: DHA_ECLAIMS_BUILD_REFERENCE.md
Word (this doc): DHA_INTEGRATION_OUTSTANDING.docx — ./docs/build-outstanding-docx.sh

Purpose: One place to see what is left, what blocks you, and rough effort to reach DHA witness UAT and certification honesty. Updated 2026-10-26.

## 1. Progress at a glance

| Lens | Estimate | Notes |
| --- | --- | --- |
| Go-live witness checklist (3 SHA funds) | ~45% complete | SHIF OP submit proven; PHC, ECCIF, SHIF IP not witnessed end-to-end |
| eClaims build phases A–J | ~55% complete | A, B, C, I done; D–H, J partial |
| Full integration matrix (18 rows) | ~50% live/partial | Excludes M-Pesa; several rows sandbox-only by design |
| Dev effort to “witness-ready” | ~15–25 person-days | Assumes 1 integration dev + clinical UAT time; excludes waiting on DHA |
| Calendar time | 4–10 weeks | Dominated by DHA IP test CR, witness scheduling, SHR OTP/test phone, optional hardware |

Effort codes: S = ≤1 day · M = 2–4 days · L = 5–10 days · XL = 10+ days or major programme.

## 2. Already done (do not rebuild)

Use for portal honesty and assessor narrative.

| Area | Evidence |
| --- | --- |
| OAuth, CR search, FR, HWR search, claim doctor resolve | Admin preflight PASS; smoke scripts |
| Eligibility, parent/sub-benefits, interventions | Patient SHA card; test-afyaconnect-eclaims-read.js |
| Claims contacts + OTP, start visit, sessions DB | Chart flow; sha_eclaims_sessions |
| SHIF outpatient visit → lines → attachments → submit | UAT Oct 2026; claim ref in chart history |
| Preauth adapter | POST /preauths, cancel /preauths/cancel (witness payload still tuning) |
| Add line, billing line, preview, submit readiness, claim history | Chart + API |
| SHR/FHIR publish path, encounter/lab hooks | TaifaCare journey (consent OTP may need DHA test SIM) |
| Witness tracks + IP readiness probe | Preflight + chart + test-afyaconnect-eclaims-ip-readiness.js |

## 3. Outstanding — required for DHA witness UAT

These map directly to go-live UAT checklist.

| # | Witness item | HMIS today | Work remaining | Effort | Blocker |
| --- | --- | --- | --- | --- | --- |
| W1 | PHC capitation full path | APIs wired; Capitation visit fund on chart | Run end-to-end on UAT; fix national body errors if any; record evidence | S–M | Clinical UAT time |
| W2 | SHIF OP (repeat for assessor) | Proven once | Repeat add/retire/switch + attachments; HIE smoke log | S | None |
| W3 | SHIF preauth (normal + specialty + cancel) | /preauths wired | Find intervention with needsPreauth; complete multipart fields per Postman; cancel witness | M | UAT intervention data |
| W4 | SHIF IP visit + discharge | IP discharge API + chart labels | End-to-end IP claim | M | DHA: IP test CR with SHA-07 / IP sub-benefits (DHA_UAT_CR_TEST_IDS.md) |
| W5 | ECCIF emergency visit + claim | Emergency visit fund | Emergency doctor consent + documentation fields; submit within 24h rules | M–L | DHA scenario validation |
| W6 | Claim management (add / retire / switch) | Buttons wired | Witness all three on active visit with national ack | S | None |
| W7 | Biometrics consent (optional checklist) | iframe + auth_guid path | HealthID agent, AFYACONNECT_BIOMETRICS_*, workstation test | M–L | Hardware + env |
| W8 | TaifaCare strip (CR → SHR → encounter) | Documented | Close SHR OTP on safe test phone; publish read-back | S–M | DHA test SIM policy |

Critical path for calendar: W4 (IP) waits on afyaconnect.dha@gmail.com — not HMIS dev capacity.

## 4. Outstanding — product / certification (not all witness-mandatory)

| # | Feature | Status | Work remaining | Effort | Blocker |
| --- | --- | --- | --- | --- | --- |
| P1 | Client Registry register/update (national create) | Not wired | CR create/update APIs + registration UX | L | DHA API + workflow sign-off |
| P2 | Terminology (OCL) national lookup | Not wired | Adapter + prescribing/diagnosis pickers | M–L | Subscription + spec |
| P3 | HPT live medicines | Sandbox catalogue only | National HPT API + pharmacy alignment | L | DHA product |
| P4 | HIE inbound (attestation / push) | Sandbox stub | Webhook or poll + reconciliation UI | L–XL | DHA channel |
| P5 | FHIR Kenya IG validator in admin | Partial publish | Validator step before live SHR send | M | Validator service |
| P6 | IDSR / DHIS2 live national pipes | Local export/alerts only | Credentials, org units, retry policy | XL each | MoH programmes |
| P7 | HL7 v2 ORU national | Outbox evidence | Only if DHA mandates; FHIR is primary | M | Policy |
| P8 | Preauth specialty payloads (surgical/oncology/renal) | Normal path only | Form fields + attachments per preauths doc | M | Postman + UAT data |
| P9 | Inpatient UX (ward context) | Chart fund type only | Optional: link admission/encounter → IP visit wizard | M | Product choice |
| P10 | Reporting SHA sandbox vs national | Both exist | Train staff: sandbox ≠ national visit submit | S | Documentation only |

## 5. Phase map (build reference) — what’s left

| Phase | Title | Status | Remaining |
| --- | --- | --- | --- |
| D | Claims consent (OTP / biometrics) | Partial | Biometrics production; edge cases on OTP |
| E | Start visit (all fund types) | Partial | PHC/ECCIF witness; IP when CR available |
| F | Pre-authorization | Partial | Specialty + elective payloads; witness cancel |
| G | Lines, retire, switch, attachments | Partial | Witness repeats; billing sync polish |
| H | Submit / discharge / close | Partial | IP discharge witness; close visit repeats |
| J | HWR (done), OCL, HPT | Partial | OCL + HPT only |

Phases A, B, C, I — treat as complete for UAT scope.

## 6. Suggested delivery order (effort sequencing)

Now (no DHA wait)     → W2, W6, W1, W3 (if preauth intervention found), W8
Parallel              → Email DHA for W4 (IP CR); schedule witness demo
When IP CR arrives    → W4 (+ re-run ip-readiness script exit 0)
Before witness demo   → W5 ECCIF; W7 if biometrics required on checklist
Post–witness / cert   → P1, P4, P5, P2/P3 as subscribed products require

## 7. Rough timeline scenarios (1 FTE integration dev)

| Scenario | Assumptions | Calendar |
| --- | --- | --- |
| A — Optimistic | DHA IP CR within 1 week; 2 dedicated UAT days/week | 3–4 weeks to witness-ready |
| B — Likely | IP CR 2–4 weeks; ECCIF/preauth iteration | 6–8 weeks |
| C — Stretched | IP CR late; biometrics + ECCIF rework | 10+ weeks |

Add 1–2 weeks after successful witness for DHA certification review (outside HMIS).

## 8. How to verify progress (repeatable)

| Check | Command / UI |
| --- | --- |
| All smokes | Administration → Run preflight |
| OP vs IP packages | node scripts/test-afyaconnect-eclaims-ip-readiness.js (exit 2 = OP-only today) |
| Witness tracks | Patient chart → UAT witness tracks |
| National claim evidence | Chart → National claim history + HIE smoke recorder |

## 9. Related documents

| Document | Use |
| --- | --- |
| DHA_AFYACONNECT_INTEGRATION_COVERAGE.md | Full feature matrix + test process |
| DHA_UAT_CR_TEST_IDS.md | Test patients; inpatient gap |
| DHA_UAT_TAIFACARE_HIE_TEST_JOURNEY.md | Clinical HIE strip |
| DHA_AFYACONNECT_GO_LIVE_PLAN.md | Ops, env, credentials |

## Changelog

| Date | Change |
| --- | --- |
| 2026-10-26 | Initial outstanding / effort document (AZ CarePlus UAT state) |